| Student Full Name: Seokwon Hong | CEG No.: CEG08111244 |
| --- | --- |
| Specialism Subject: Animation & Film | Submission Date: Monday 24 May 9-10am |
| EXT DIP 2 A |  |
| Project Title: Rashomon VR |  |

| Date Week Beginning | Important Dates & Suggested areas to work per week | Activity | Resources |
| --- | --- | --- | --- |
| 08 MAR Week 1 | Consolidation Practice. Initial investigation | Watch the movie ‘Rashomon’ (1950) -Kurosawa Akira. Read the original ‘Rashomon’ -Akutagawa Ryunosuke. | Book ‘Rashomon’- written by Akutagawa Ryunosuke Movie ‘Rashomon’ - directed by kurosawa akira |
|  | Research Week | WED: ‘Rashomon’ report + Pippin Peacock report THUR: ‘Distortion’ report + Francis Bacon + another artist – Artist responses +Georgia Adams, Audrey Whelan reports FRI: Proposal & Timetable finish SAT: Presentation finish SUN: Supplement | Ted - The fiction of memory, Elizabeth Loftus 12 Angry Men (1957) – directed by Sidney Lumet Anna Maria. W, Francis Bacon, 2009, Yekyung, 1-119p |
| ffNotes: | You will be expected to use this time to enhance your FMP primary research relevant to your themes. Keep all reflective notes, drawings, photos and if you can access exhibitions/museums– tickets, leaflets/photos Have you evaluated and reflected in your blog? Don’t forget bibliography & cross referencing. |  |  |
| 22 MAR Week 3 | Presentation of Proposal, Weekly Action Plan & Timetable, Bibliography & Submission to blog (Day depending on your specialism) Tutor Formative Assessment | Compare interactive, interactive VR games and make reports Research second Artist: It could be Yue Minjun Research third Artist: VR | Oculus Quill Home After War Primary resource- visit Yue Minjun in Korea |
| Notes: | Easter |  |  |
| 29 MAR Week 4 Easter Vacation | Experimental Investigation Development | VR game making starts Move Korea to the U.K Use Quill and report Thumbnail drawing Character design Synopses Animatic sequence Sculpting (Blender) | Photoshop InDesign ’Blender 2.91 |
| Notes: |  |  |  |
| 5 APR Week 5 Easter Vacation | Experimental Investigation Development | VR game making starts!! +Wrapping and Poly colouring(texturing). Retopologing. | Unity Engine Oculus VR Blender UV MAP |
| Notes: | You will be expected to use Easter Vacation to enhance your FMP research and development. |  |  |
| 12 APR Week 6 | Experimental Investigation Development | VR game making starts!! Blender animation making: Lion’s view and man’s view. (Rigging and animating) Lip sync adding (mouth moving = facial expressions) Animation rendering | Maximo(?) Blender 2.91 ver. Mark Seam |
| Notes: | --- Formative |  |  |
| 19 APR Week 7 | Synthesis of ideas Tutor Formative Assessment | VR game making starts!! Changing platform from MAC to Window Making VR foundation on unity ex) VR camera, VR rig. Programming for the VR hands | USB Oculus Quest Microsoft Visutal Studio |
| Notes: |  |  |  |
| 26 APR Week 8 | Synthesis of ideas | Finish making VR + making the game poster, advertisement *In case of enough time Exporting Blender mesh and texture into Unity, but not the animation. | Photoshop Unity shading system Blender 2.91 |
| Notes: |  |  |  |
| 3 MAY Week 9 | Production | Upload game and take feedback. Report + Animation exporting | Steam Unity animator |
| Notes: |  |  |  |
| 10 MAY Week 10 | Production and presentation | Presentation, Self-assessment Finding appropriate game sound effects – Tryst ’Man’s viewpoint – Lion’s viewpoint (Scene changing), Programming. | Fumio Hayasaka’s ‘TRYST’ on YouTube. ’Microsoft’s Visual Studio. |
| Notes: |  |  |  |
| 17 MAY -23 MAY Week 11 | Presentation And Evaluation | Finish Self- assessment - Voice over(dubbing) with Ali. - Adding voice into the game engine. - Making game menus (UI design). {start scene and ending scene} - Subtitle making - Haptic senses making (electronic signals through the hands) - Presentation preparation. - Game environment&mood making. - Blog writing. - Peer&Self-assessment. | Zoom voice recorder Unity UI – Canvas system Unity haptic system Unity lighting system Microsoft PowerPoint(?) Premiere Pro for sound editing Microsoft’s Visual Studios |
| Week 12 24 MAY 25 MAY | 9am 9am | Final deadline for submission of all work: You will need to submit all work via your blog Final deadline for online self-assessment unit 4/unit 13 |  |
| Notes: | Registration required |  |  |
| 31 MAY Week 13 |  | Assessment Week Students receive referral notification by Tuesday 1st June between 2-5pm to be completed by Thursday 10TH June midday 12pm |  |
| Notes: | Registration required |  |  |
| 7 JUNE Week 14 10 June (Wednesday) | 12pm (midday) | Final deadline for submission of referral work: |  |
| Notes: | Registration required |  |  |
| 14 JUNE Week 15 18 June (Friday) |  | Final Grades awarded: Sturton Street, Studio 16 & after in SS Canteen for refreshments and photos | End of term party!? Prom? Student committee to organise see your reps! |
| Notes: | Registration required |  |  |
| Notes: | All personal effects to be removed from studios Please be aware these cannot stored , but recycled/given to charity |  |  |